## Sheet1
Why we shouldn't miss the opportunity
Influence from Nadeeka/CEO level relationship
Engineering (Gayan) and Fintech Domain (Prabodha) Experience we have
We have to solve a general problem (CRM) not a very complex problem
Product engineering (either own CRM or Open Source) has become simplified with AI
Challenges
Founders have to carry some operational burden at the begining
Finding the right SME in CRM domain
Option 1 — Build the system yourself (Intellect develops the full solution)
Pros
No dependency risk on an external vendor.
Better customer trust: Siyapatha knows they are dealing directly with Intellect.
Enables future productisation → can sell the same CRM to other NBFIs.
Higher profitability long-term (implementation + support + enhancements).
Full control of the architecture, quality, timelines, and customer experience.
Cons
Highest resource commitment (BA, PM, Devs, QA, Integrations)
Delivery Risk is with Intellect
Option 2 — White-Label a Partner’s CRM but Deliver as Intellect
Pros
System already exists, proven, and used by real customers.
Intellect owns the client relationship
Lower risk & lower engineering load
Cons
You are dependent on the partner’s capability
Lower long-term value than owning our own product
Lower profitability
Option 3-Consortium / Tri-party Agreement (Intellect + Partner + Customer)
Pros
Risk is shared
Good for complex projects (call centre + CRM etc)
Cons
Complicate governance
Decision making is slow
Option 1 - Way Forward
Build on based on an existing framework like suite CRM
Solution Overview /Feature Diagram /SRS
Caculate the effort required to develop a basic product /MVP for a NBFI
Questions to the Business
Current nature and use of Iphonik System
Current Business Process
How many officers /working hours
What is manual /What is handled using Iphonik
Is call center centralized / Head office only or Island Wide
How does call center users are getting customer information/ 360 view as of now
What are the other business cases in CRM

## RFI Questions
1 | Problem Statement
2 | Who are the users
Volume
Data Sources and readiness

## RFI
S/N | Name | Track | Primary Owner | Action items | Deadline | Reviewer | Status
1 | Introduction |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25 : Ready to Review
2 | Executive Summary |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25 : Ready to Review
3 | Poposal Solution Overview |  | Praboadha | Prabodha to complete the draft | TDB | Jeewana | 07/12/25 : - CRM Platform - Ready to Review - Call Center Platform - Draft - Integration & Anallytics - Draft
4 | Detailed Functional Capabilities |  | Praboadha/ Gayan | Praboadha/ Gayan/ Jeewana to have a meeting to finalise - 12/8/25 DL - Collect each major module functional scope (Damith to provide managers for meetings) - 15/12/2025 | 2025-12-08 | Jeewana | 07/12/25 : - Lead Management - Ready to review - Customer 360' review - Ready to review - Complaint & Case Management - Ready to Review - Call Center Capabilities - Ready to Review - Omnichannel Communication - Ready to Review
5 | System Architecture | Tech | Gayan + Dev | - Dev's NDA - Gayan should work with Dev | 2025-12-10 | Jeewana | 07/12/25 : Content structure is there, this need to changed the core modules based on SuiteCRM
6 | Integration Architecture | Tech | Gayan + Dev | - Dev's NDA - Gayan should work with Dev | 2025-12-10 | Jeewana | 07/12/25: Consider integration with CoreBanking Finacle
7 | Reporting Analytics | Tech | Gayan | - Dev's NDA - Gayan should work with Dev | 2025-12-10 | Jeewana | 07/12/25: - Ready to review
8 | Non-Function Requirement |  | Gayan | Gayan to complete | 2025-12-10 | Jeewana | 07/12/25: draft
9 | Implemetation Approach & Timeline |  | Gayan | Praboadha/ Gayan/ Jeewana to have a meeting | 2025-12-08 | Jeewana | 07/12/25: draft
10 | Support and Maintainance Model |  | Praboadha |  |  | Jeewana | 07/12/25: draft
11 | Value Added Enhancement & Road |  | Gayan | Gayan to complete | 2025-12-10 | Jeewana | 07/12/25: draft
12 | Compliance Statements |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25: ready to review
13 | Assumptions & Dependencies |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25: ready to review
14 | Pricing Strutctre and Commercials |  | Praboadha/ Gayan/ Jeewana | Praboadha/ Gayan/ Jeewana to have a meeting | 2025-12-13 | Jeewana | 07/12/25: draft
15 | Terms & Conditions |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25: ready to review
16 | Appendix & Document Attachment |  | Praboadha | Jeewana to review | 2025-12-08 | Jeewana | 07/12/25: ready to review
Critical items
1 | Praboadha/ Gayan/ Jeewana to have a meeting to finalise functional scope
2 | Dev's NDA
3 | Implemetation Approach & Timeline
4 | Pricing Strutctre and Commercials
Key Gaps
1 | State of Call Center Operation, do we need have a new one?
2 | Amount of data Client is willing to expose to CRM in order store inside CRM or as APIs wise
3 | Amount of staff that in Org Chart that going engage
4 | Number of branches and accepted Pilot group size
5 | In order train staff what platforms will be available
6 | Number of organisational devices given (type of device/ OS/ Internet accessiblity)
7 | Identity and Access management
8 | Process level change implementation and management
Deadline
| 17th December 2025 | Submission
| 15th December 2025 | Final review round
| 13th December 2025 | Pricing Strutctre and Commercials
| 12th December 2025 | All technical chapters doucmentation completion
| 10th December 2025 | All technical chapters draft doucmentation completion
| 8th December 2025 | Detailed Functional Capabilities

## Project Costing
| Resource | Duration | CTC | Utilization | Cost
| Project Manager | 18 | 250000 | 0.5 | 2250000
| Tech Lead | 12 | 400000 | 1 | 4800000
| Engineer | 18 | 200000 | 2 | 7200000
| BA | 16 | 200000 | 1 | 3200000
| QA | 12 | 200000 | 1 | 2400000
Other Cost
| Suite CRM Support Package |  |  |  | 2100000
Hosting-Test Environment
21950000
|  |  |  | Contingency | 1097500
23047500
34571250