## Check List
Task Name | Assigned To
Get CRM and Portal UAT backup(app and db) to production server and configure app and db sync | CRM Team
CRM and Portal connectivity check in Production | CRM Team
Get Users, Roles and Security Groups (for Call center users) | Bank Team
Create Users, Roles and Security Groups | CRM Team
Map workflows to Users and Roles | CRM and Bank Team
ODBC user details approvals from bank | Bank Team
Move the production API's | Bank Team
All customer 360 API changes and testing in Production | CRM and Bank Team
Check CTI Integration | CRM and MIT Team
Share Production CRM Prod Domain name, LDAP server, Email server details | Bank Team
Check LDAP Integration and Email configuration in Production | CRM Team
Connect Talend ESB (production) with CRM Production | CRM and Bank Team
Move the Talend jobs from UAT to Production | CRM Team
Migrate all the data to Production | CRM Team
Verify migrated data in Production | CRM and Bank Team
Configure the daily jobs with scheduler in Production | CRM Team and Bank Team
Testing and Go Live | Bank Team